## Menu
El Dorado County ACEs Collaborative
Click on the sector name to go to that sector's plan or plans
Behavioral Health Sector
Community Sector - General
Community Sector - Hubs
Divide Sector
Education Sector
Health Sector
Public Safety Sector
South Lake Tahoe Sector
Social Services and Foster Care Sector

## Behavioral Health.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Behavioral Health |  | Increase awareness and competencies in our partner agencies regarding ACEs and Resilience. |  |  |  | Increase awareness and competencies in our partner agencies regarding ACEs and Resilience.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Provide ACEs resources to Substance Use treatment providers for youth and adults. |  | Completed and Ongoing | Stephanie Carlson, Nora | 2017-10-01 |  | Engage and train Friday Night Live youth in ACEs.
2 | Engage and train Friday Night Live youth in ACEs. |  | Not completed | Nora | 2018-06-01 |  | #REF!
3 | [6 empty] | Provide ACEs resources to Substance Use treatment providers for youth and adults.
4 | [6 empty] | 0
5 | [6 empty] | 0
6
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
21 | [6 empty] | 0
22 | [6 empty] | 0
23 | [6 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Behavioral Health.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Behavioral Health |  | Increase awareness, sensitivity and inclusivity within our agencies and then expand to community members.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Review HHSA forms to ensure inclusive language regarding marital status, gender, and family members. |  | Completed | Angie | 2017-05-01
2 | Review partner agency forms to ensure inclusive language regarding marital status, gender, and family members. |  | Completed | Ellen, Chris, Alison | 2017-07-01
3 | Facilitate awareness and provide stigma reducing flyers and information about Mental Health & lesbian, gay, bisexual, transgender, and questioning (LGBTQ) populations available in Health and Human Services Agency (HHSA) and partner agencies prior to Pride Month. |  | Completed and Ongoing | Amanda and Angie | 2017-10-01
4 | Promote A Providers Guide to LGBTQ training to partner agencies and provide 2 classes. |  | Completed and Ongoing | Stephanie | 2017-10-01
5 | Provide agency training on LGBTQ cultural awareness and skill building. |  | Completed and Ongoing | Stephanie | 2017-10-01
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Behavioral Health.3
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 3
Sector Workgroup: Behavioral Health |  | Implement trainings that reduce stigma around mental health.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1.2 | Facilitate Brief Intervention Program and skill building at El Dorado High School. |  | Completed and Ongoing | Nora, Judy | 2017-10-01
2 | Provide Mental Health First Aid (adult and youth) trainings to community members. |  | Completed and Ongoing | Arturo & Stephanie | 2017-10-01
3 | Conduct safeTALK to youth and youth leaders. |  | Completed and Ongoing | Stephanie | 2017-10-01
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Community - General.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Community - General |  | Further develop ACEs awareness and advocacy for trauma-informed policies and practices within general community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1.2 | Conduct media outreach (social media and print media) to general community on ACEs and resiliency. |  | Completed and Ongoing | Julia, Pam, Cindy | 2017-03-01
2 | Conduct community dialog re: ACES & resiliency via film series. |  | In Progress | Pam, Juline | 2017-10-05
3 | Host 1/2 day forum with cross section of community stakeholders to build understanding re: ACEs and their impact. |  | Not Completed | Pam, Julia, Cindy, Dee | 2018-08-16
4 | Host 1/2 day forum with cross section of community stakeholders to shape choices re: addressing ACEs and their impact. |  | Not Completed | Pam, Julia, Cindy, Dee | 2018-09-13
5 | Build capacity of the Community Sector Work Group. |  | Completed and Ongoing | Pam, Julia, Cindy, Dee | 2018-10-01
6 | Host 1/2 day forum with cross section of community stakeholders to make decisions re: addressing ACEs and their impact. |  | Not Completed | Pam, Julia, Cindy, Dee | 2018-10-18
7 | Create and implement an accountability plan if needed re: decisions made at forum. |  | Not Completed | Pam, Julia, Cindy, Dee | TBA as applicable
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Community - Hubs.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Community - Hubs |  | Implement universal developmental screenings for families with children birth through five years of age.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Identify the universal screening tools such as Ages and Stages Questionnaire (ASQ) and the ASQ Social Emotional Tool (ASQ:SE). |  | Completed | Kathi | 2016-10-01
2 | Promote parents and caregivers regularly monitoring their child(s) development utilizing this tool at the library or online at: e.g. English ASQ: http://tinyurl.com/6pe54lv English ASQ: Social Emotional: http://tinyurl.com/7ff5jve |  | In Process | Kathi, Andrea, Amber, Elizabeth, Jeanne, Carolyn | 2018-06-30
3 | Family Engagement Specialist will score tool and encourage parents/caregivers to: continue monitoring, connect to resources or refer to Public Health Nursing for further assessment as needed. |  | In Process | Elizabeth | 2018-06-30
4 | Public Health Nurse will assess the child's development and refer as appropriate for follow-up services. |  | In Process | Amber | 2018-06-30
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23

## Community - Hubs.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Community - Hubs |  | Community Hub staff will use a trauma informed approach in working with parents and caregivers.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Provide training to Hub Teams on using a trauma-informed approach in working with clients. |  | In Process | Amber, Kathi, Andrea | 2018-06-30
2 | Hub Teams will use a trauma-informed approach with parents and caregivers accessing services at Community Hubs. |  | In Process | Kathi, Andrea, Elizabeth, Jeanne, Amber, Carolyn | 2018-06-30
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Community - Hubs.3
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 3
Sector Workgroup: Community - Hubs |  | Provide education to community champions on ACEs, their effects on social and physical health, and importance of and how to build resiliency.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Convene Community Champions at a town hall meeting to describe the importance of resilience, trauma informed care and ACEs. |  | Not Completed | Kathi, Andrea, Heather | 2018-10-01
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Divide.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Divide |  | Increase ACEs awareness and education in the Georgetown Divide community. |  |  |  | Increase ACEs awareness and education in the Georgetown Divide community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Create and maintain a Facebook page for Divide ACEs. |  | Completed and Ongoing | Liz | 2016-08-15 |  | Create and maintain a Facebook page for Divide ACEs.
2 | Conduct ACEs Informational Presentations to Faith Community on the Divide. |  | Completed | Lucy, Cindy | 2016-10-01 |  | Conduct ACEs Informational Presentations to Faith Community on the Divide.
3 | Conduct ACEs Informational Presentations to entire Black Oak Mine Union School District staff, school board and administration (i.e. Paper Tigers). |  | In Process | Lucy, Jennifer, Carolyn, Sam, Jeremy | 2018-10-01 |  | Conduct ACEs Informational Presentations to entire Black Oak Mine Union School District staff, school board and administration (i.e. Paper Tigers).
4 | Conduct ACEs Informational Presentations to Head Start and Preschool teachers on the Divide. |  | Not Completed | Lucy, Liz, Monica | 2018-10-01 |  | Conduct ACEs Informational Presentations to Head Start and Preschool teachers on the Divide.
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Divide.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Divide |  | Promote trauma-informed practices within the Divide community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Create and implement a survey to assess self-care practices and needs in elementary school teachers and parents. |  | Not Completed | Monica, Samantha | 2018-01-01
2 | Work with Faith-based community on the Divide to a create and aument meal distribution centers for families. |  | In Process | Lucy, Cindy | 2018-06-01
3 | Train staff at Northside School in Mindfulness practices. |  | In Process | Jennifer, Samantha, Monica | 2018-10-01
4 | Train staff at Georgetown School in Mindfulness practices. |  | In Process | Jennifer, Samantha, Kim | 2018-10-01
5 | Develop Action Plans to make all distric schools be trauma-informed. |  | In Process | Lucy, Jennifer, Monica, Sam | 2018-10-01
6 | Train all treachers in district in Positive Behavior Interventions and Supports. |  | In Process | Jeremy, Wendy | 2018-10-01
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Education.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Education |  | Build capacity for ACEs work group in the education community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Develop a meeting schedule that meets the workgroup needs and allows for reporting at quarterly ACEs Collaborative meetings. |  | Completed and Ongoing | Elizabeth | 2017-06-30
2 | Develop committee leadership structure, choose a chair and co-chair to support committee effectiveness. |  | Not Completed | Tara, Elizabeth, Michelle, Mary, Angie, Jill | 2017-12-01
3 | Identify a meeting time and location which meets the majority of the committee's scheduling needs. |  | Completed and Ongoing | Tara, Elizabeth, Michelle, Mary, Angie, Jill | 2018-01-01
4 | Send invitation to all K-12 principals, school nurses and counselors inviting them to the meeting. |  | In Process | Elizabeth and all workgroup members | 2018-04-01
5 | Build administrator/school leadership by sharing ACEs and resiliency information with educational leaders. |  | Completed and Ongoing | Angie, Jill and Tara | 2018-06-01
6
7
8
9
10
11
12
13
14
15

## Education.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Education |  | Increase ACEs awareness and trauma-informed practices in the education community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Develop one pager to describe ACEs Collaborative for educational community. |  | Completed | Lynnan, Judy, Melissa & Elizabeth | 2017-09-01
2 | Identify best practices to develop trauma-informed K-12 school. |  | In Process | Rochelle - (middle school) Kelly (high school), Michelle (k-8) | 2018-06-01
3 | Explore possibility of showing "Paper Tigers" movie at school sites for school staff. |  | Not Completed | Tara, Elizabeth, Michelle, Mary, Angie, Jill | 2018-10-01
4 | Explore feasibility of showing "Resilience" movie to school staff. |  | Not Completed | Tara, Elizabeth, Michelle, Mary, Angie, Jill | 2018-10-01
5 | Share trauma informed care training information with Education sector |  | In Process and Ongoing | Elizabeth | 2018-10-01
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Health.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Health |  | Increase ACEs awareness and education in the healthcare community.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Provide ACEs and trauma-informed care information to home visitors. |  | Completed | Melissa, Lynnan, Cindy | 2017-02-15
2 | Provide ACEs and trauma-informed care information to jail and JTC staff. |  | Completed and Ongoing | Judy, Dora, Theresa | 2017-07-27
3 | Conduct ACEs in-service at the Divide Wellness Center. |  | Completed | Amber, Cindy | 2017-10-01
4 | Explore opportunities to provide and ACEs in-service at Shingle Springs Tribal Health. |  | Completed and Ongoing | Kathleen, Amber | 2017-10-01
5 | Provide ACEs and trauma-informed care information to WIC staff. |  | Completed | Cindy, Kathleen, Ellen | 2017-10-01
6 | Provide ACEs education at the Head Start Health Advisory Committee Meeting. |  | In Process | Lynnan, Amber, Kimberly | 2018-05-01
7 | Provide on-going education for School Nurses on ACEs and resiliency. |  | In Process | Lynnan, Valerie | 2018-06-01
8 | Conduct ACEs in-service for the El Dorado Community Health Center. |  | Not Completed | Amber, Lynnan, Rebecca | 2018-10-01
9 | Conduct ACEs in-service at Marshall Medical Center - OB/GYN. |  | In Process | Lynnan, Nancy, Christine, Donna | 2018-10-01
10 | Conduct ACEs in-service at Marshall Medical Center - Pediatrics. |  | In Process | Lynnan, Nancy, Teresa, Donna | 2018-10-01
11 | Conduct ACEs in-service at Marshall Medical Center -Family Practice. |  | In Process | Lynnan, Nancy, Donna | 2018-10-01
12 | Conduct ACEs in-service at Marshall Medical Center - ER. |  | In Process | Lynnan, Nancy, Kim, Donna | 2018-10-01
13 | Conduct ACEs in-service at Marshall Medical Center - MD Meeting. |  | Completed | Nancy | 2018-10-01
14 | Provide in-service with emergency medical responders. |  | In Process | Lynnan, Nancy | 2018-10-01
15 | Explore opportunities to provide in-services at area urgent care medical centers. |  | Not Completed | Lynnan | 2018-10-01
16 | Provide on-going education for staff in Public Health Nursing on ACEs and resiliency. |  | In Process | Lynnan, Melissa | 2018-10-01
17
18
19
20
21
22
23

## Health.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Health |  | Build capacity for area medical providers to use ACEs screening tools, resource list, brief intervention tools and incorporate trauma-informed services into their practices.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Develop concrete examples of how it will benefit clients. |  | In Process | Kathleen, Val, Cindy, Dora | 2018-06-01
2 | Develop and/or share local resource list. |  | In Process | Amber | 2018-06-01
3 | Develop concrete examples of how to provide self care. |  | In Process | Cindy, Lynnan, Amber, Dora | 2018-06-01
4 | Present best practice toolkit for practical application purposes. |  | Not Completed | Lynnan, Melissa | 2018-10-01
5 | Explore brief intervention tools and share. |  | Not Completed | Cindy | 2018-10-01
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Health.3
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 3
Sector Workgroup: Health |  | Start to implement a trauma-informed approach in providing healthcare services on the Western Slope.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Community Hub Health Staff will utilize a trauma-informed approach to working with clients. |  | Completed and Ongoing | Lynnan, Amber | 2017-05-01
2 | Provide a trauma-informed approach with clients that interact with Public Health Nursing Staff. |  | Completed and Ongoing | Lynnan | 2018-01-01
3 | Review current Public Health screening STD form and make it trauma sensitive. |  | In Process | Teresa | 2018-03-01
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Public Safety.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: Public Safety |  | Increase workgroup members to include fire, Sheriff's Office (EDSO), and Courts.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Contact EDSO for name of officer he recommends as sector group member. |  | In Process | Judy Knapp, Theresa Nannery | 2018-10-01
2 | Contact Jackie from Courts for potential sector group member. |  | Not Completed | Judy Knapp, Theresa Nannery | 2018-10-01
3 | Contact the Fire Department, for name of potential sector group member. |  | In Process | Judy Knapp, Theresa Nannery | 2018-10-01
4 | Contact CHP for name of potential sector group member |  | Not Completed | Judy Knapp, Theresa Nannery | 2018-10-01
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Public Safety.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: Public Safety |  | Increase ACEs awareness and education among public safety partners.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Provide Animal Services with training on ACEs, resiliency, and trauma-informed approach. |  | Completed | Alexis Shaw, Judy Knapp | 2017-08-01
2 | Provide Community Corrections Center/Probation staff with training on ACEs, resiliency, and trauma-informed approach. |  | Not Completed | Karla Kowalski, Judy Knapp | 2018-03-01
3 | Provide Placerville Police Department with training on ACEs, resiliency, and trauma-informed approach. |  | Not Completed | Jason Alger, Judy Knapp | 2018-10-01
4 | Provide Courts with training on ACEs, resiliency, and trauma-informed approach. |  | Not Completed | Court, Judy Knapp, Sheila Silan | 2018-10-01
5 | Provide Fire with training on ACEs, resiliency, and trauma-informed approach. |  | Not completed | Fire, Judy Knapp | 2018-10-01
6 | Provide EDSO with training on ACEs, resiliency, and trauma-informed approach. |  | Not Completed | EDSO, Judy Knapp, Sheila Silan | 2018-10-01
7 | Provide CHP with training on ACEs, resiliency, and trauma-informed approach. |  | Not Completed | CHP, Judy Knapp | 2018-10-01
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## South Lake Tahoe.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 1
Sector Workgroup: South Lake Tahoe |  | Involve Pediatricians, Primary Care and Emergency Room Physicians to screen for ACEs, get familiar with resources available in the SLT community, and incorporate trauma-informed practices.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Conduct a 20 minute presentation on ACEs, Resiliency and trauma-informed practices for providers and staff at Barton Clinic. |  | Completed | Audrey H., Josefina S. | 2016-11-10
2 | Conduct a 20 minute presentation on ACEs, Resiliency and trauma-informed practices for providers and staff at Barton Pediatrics. |  | Completed | Audrey H., Josefina S. | 2017-02-01
3 | Conduct a 20 minute presentation on ACEs, Resiliency and trauma-informed practices for providers and staff at Barton OB clinics. |  | Completed and Ongoing | Audrey H., Josefina S. | 2017-02-01
4 | Identify current Social-Emotional screening tools used by physicians. |  | Completed and Ongoing | Audrey H., Josefina S. | 2018-02-01
5 | Schedule follow up meetings with the clinics to discuss if and how the ACEs questionaire was implemented including successes and barriers etc. |  | Completed and Ongoing | Audrey H., Josefina S. | 2018-05-01
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23

## South Lake Tahoe.2
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 2
Sector Workgroup: South Lake Tahoe |  | Promote Behavioral Health assessment to include ACEs screening and El Dorado County Behavioral Health trauma informed - Dialectical behavior therapy (DBT).
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Implement ACES tool within treatment planning session, educating clients as to risks and resiliency goals. |  | Completed | Sabrina | 2017-01-01
2 | Utilize DBT (trauma senstive practice) in all theraputic settings. |  | Completed and Ongoing | Sabrina | 2018-01-01
3 | Encourage other HHSA programs and external agencies to implement ACEs screening and resiliency practices. |  | Completed | Sabrina | 2018-10-01
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## South Lake Tahoe.3
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 3
Sector Workgroup: South Lake Tahoe |  | Infuse trauma-informed and resiliency practices at Lake Tahoe Unified School District (LTUSD) schools.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Educate counselors and administration on ACEs and trauma-informed practices. |  | Completed | Sabrina, Anastasia | 2018-01-01
2 | Promote and educate on Resiliency Practices with teachers. |  | Completed | Natalie | 2018-01-01
3 | Present at the LTUSD Board meeting ways to promote Resiliency Practices at schools. |  | Completed | Sabrina | 2018-01-01
4 | Meet with LTUSD Counselors and Superintendent to educate about ACEs and encourage trauma-informed intervention practices at LTUSD. |  | Completed | Sabrina | 2018-01-01
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## South Lake Tahoe.4
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project: |  | Objective: |  | 4
Sector Workgroup: South Lake Tahoe |  | Identify Coommunity Partners that are interested in engaging in ACES and Resiliency Practices.
Specific Tasks |  |  | Status | Person/s Designated | Timeline
1 | Invite COE Services Coordinator to SLT Sector meeting. |  | Completed | Josefina S. | 2016-10-14
2 | Identify community partners that are or are willling to impliment resilinency pratices. |  | Completed | Anastasia | 2016-11-16
3 | Identify a champion at Barton to promote use of Screening tool and trauma-informed practices. |  | Completed | Josefina S., Audrey | 2017-05-01
4 | Schedule meetings to discuss current practices and offer education on implementing resiliency interventions. |  | Completed | Anastasia | 2017-06-01
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Social Services & Foster Care.1
El Dorado County ACEs Collaborative
Action Plan
Back to Menu
Project |  |  | Objective: |  | 1
Sector Workgroup: Social Services and Foster Care |  |  | Through education, raise awareness about the impacts of trauma (ACEs) and with a common understanding and shared language, inform/improve practice throughout our sector among our staff and the people that we serve.
Specific Tasks |  |  |  | Status | Person/s Designated | Timeline
1 | Incorporate ACEs and Resiliency information into the new El Dorado County Resource Family Approval training. |  |  | Completed and Ongoing | Juline | 2017-01-30
2 | Provide training on ACEs and Resiliency with Judy Knapp to Resource Families (Foster Parents). |  |  | Completed | Juline | 2017-03-01
3 | Provide an ACEs introduction, ongoing education, information and awareness of ACEs to Income Maintenance staff. |  |  | Completed | Nina, Deb | 2017-05-30
4 | Provide ACEs and Trauma-Informed Care information to Resource Family Approval staff. |  |  | Completed | Michael | 2017-06-30
5 | Create trainings to be used during CASA New Advocate trainings as well as for Continuing Education classes. |  |  | Completed and Ongoing | Julia | 2017-06-30
6 | Increase awareness and education regarding ACEs, Trauma-Informed Care and Resiliency for Courts/Minors counsel/County Counsel. |  |  | Completed | Kathy | 2017-09-01
7 | Train Court Appointed Special Advocates (CASA) staff on what ACEs is and how it effects each aspect their jobs. Tailor information to recruiting/fundraising/and program. |  |  | Completed and Ongoing | Julia | 2018-06-30
8 | Provide ACEs and Trauma-Informed Care information to School Attendance Review Board members. |  |  | Not Completed | Sheila | 2018-09-01
9 | Provide training on ACEs and Resiliency for Foster Awareness Board and members. | Foster Awareness Network (FAN) Invite FAN board and members to attend FKCE training in January |  | In-Process | Juline | 2018-10-01
10 | Provide ACEs and Trauma-Informed Care information to all district Local Control and Accountability Plan (LCAP) teams. |  |  | Not Completed | Sheila | 2018-10-01
11 | Provide ACEs and Trauma-Informed Care information to all Charter Staff. |  |  | Not Completed | Sheila | 2018-10-01
12 | Provide ACEs and Trauma-Informed Care information to In Home Support Services (IHSS) staff. |  |  | Not Completed | Laura | 2018-10-01
13 | Provide ACEs and Resiliency Awareness to Foster Family Agency staff, care givers, and families. |  |  | Completed and Ongoing | Juline, Sara | 2018-10-01
14 | Provide ongoing education for staff in Child Welfare Services on ACEs, Trauma-Informed Care and Resiliency. |  |  | Completed and Ongoing | Kathy | 2018-10-01
15 | Provide ACEs and Trauma-Informed Care information to Adult Protective Services staff. |  |  | Not Completed | Laura | 2018-10-01
16 | Provide ACEs and Trauma-Informed Care information to Public Guardian staff. |  |  | Not Completed | Pam | 2018-10-01
17 | Provide ACEs and Trauma-Informed Care information to all Area Agency on Aging staff. |  |  | Not Completed | Michelle | 2018-10-01
18 | Provide information to IHSS Providers on ACEs and Trauma-Informed Care information through the IHSS Public Authority newsletter. |  |  | Not Completed | Joseph | 2018-10-01
19 | Provide ACEs and Trauma-Informed Care information to all Adult Day Services staff. |  |  | Not Completed | Michelle | 2018-10-01
20 | Provide ACEs and Trauma-Informed Care information to the Advisory Council to the Area Agency on Aging (Commission on Aging). |  |  | Not Completed | Michelle | 2018-10-01
21 | Explore mandatory training for all Shingle Springs Tribal employees; combine ACEs information with Mental Health First Aid to be offered twice a month to tribal members, casino employees and the community. |  |  | Not Completed | Arturo | 2018-10-01